## Sheet1
CONTINGENCY PLANNING
No. | Type of contingency reviewed | Current status | Action plan | Who is Responsible | Target Date | Status
1 | Server outage | No known issues | Establish redundancy in servers, implement automatic failover system, establish communication channels with users | Project team and Client (after take over the system) | NA | Not started
2 | Data breach | No known issues | Implement regular security updates, perform penetration testing, encrypt sensitive data, establish incident response plan | Project team and Client (after take over the system) | NA | Not started
3 | Technical bug | Some minor bugs reported by users | Establish bug-tracking system, prioritize bugs based on severity, develop and deploy fixes | Project team and Client (after take over the system) | NA | Not started
4 | Service interruption | No known issues | Establish backup servers, implement automatic failover system, establish communication channels with users | Project team and Client (after take over the system) | NA | Not started
5 | Third-party service failure | No known issues | Establish contingency plan for critical third-party services, monitor performance of third-party services, maintain backups of critical data | Project team and Client (after take over the system) | NA | Not started
6 | Application failure | No known issues | Establish monitoring and alerting system for application errors, implement automatic system restarts, develop contingency plan for critical application components | Project team and Client (after take over the system) | NA | Not started
7 | Power outage | No known issues | Establish backup power sources, implement automatic failover system, establish communication channels with users | Project team and Client (after take over the system) | NA | Not started
8 | Database failure | No known issues | Establish regular backups, implement automatic failover system, establish communication channels with users | Project team and Client (after take over the system) | NA | Not started
9 | Website defacement | No known issues | Implement website security measures such as SSL certificates, web application firewall, and anti-malware software, maintain website backups, establish communication channels with users | Project team and Client (after take over the system) | NA | Not started
10 | Network outage | No known issues | Establish redundancy in network equipment, implement automatic failover system, establish communication channels with users | Project team and Client (after take over the system) | NA | Not started
11 | Malware infection | No known issues | Implement malware prevention measures such as antivirus software, malware scanners, and firewall rules, maintain website backups, establish communication channels with users | Project team and Client (after take over the system) | NA | Not started
12 | Cyber attack | No known attacks | Implement cybersecurity measures such as regular penetration testing, multi-factor authentication, and intrusion detection systems, maintain website backups, establish communication channels with users | Project team and Client (after take over the system) | NA | Not started
PREPARED BY: CHECKED BY: APPROVED BY: