## HOURLY RATE
Position | Name | Hourl Rate | Reference/s
Project Manager | Mikedale Dellera | 341 | Project manager salary in Philippines (indeed.com)
Product Owner | Wilkin Caducio | 413 | Product owner salary in Philippines (indeed.com)
Documentation Manager | Princess Joy Ferrer | 178.16 | Documentation manager salary in Philippines (indeed.com)
Scrum Master | Jakerson Bemrudo | 485.95 | Scrum Master Salary Manila, Philippines - SalaryExpert
Jr Developer | Rark Mowen Alcantara | 254 | Software engineer salary in Philippines (indeed.com)
QA Tester | Carl James Garcia | 271 | https://ph.indeed.com/career/quality-assurance-tester/salaries?from=top_sb
Trainer salary in Philippines (indeed.com)

## LAPTOP DV
Depr. Rate (Laptop) | Years
25% | 1.67
| Laptop Price | Years Used | Current Value (after depriacted by years) | Depr. Value | Working Hours | DV per hour | LAPTOP DV(NAME)
Mikedale Dellera | 70000 | 2 | 35000 | 14612.5 | 389 | 37.5643
Princess Joy Ferrer | 43000 | 2 | 21500 | 8976.25 | 387 | 23.1944
Wilkins Caducio | 35000 | 1 | 26250 | 10959.375 | 446 | 24.5726
Jakerson Bermudo | 50000 | 3 | 12500 | 5218.75 | 699 | 7.466
Carl James Garcia | 47000 | 3 | 11750 | 4905.625 | 242 | 20.2712
Rark Mowen Alcantara | 70000 | 3 | 17500 | 7306.25 | 720 | 10.1476

## BUDGET SUMMARY
|  |  | Mikedale Dellera |  |  | Wilkins Caducio |  |  | Princess Joy Ferrer |  |  | Jakerson Bermudo |  |  | Rark Mowen Alcantara |  |  | Carl James Garcia
LAPTOP DV |  |  | 37.5643 |  |  | 24.5726 |  |  | 23.1944 |  |  | 7.466 |  |  | 10.1476 |  |  | 20.2712
HOURLY RATE |  |  | 341 |  |  | 413 |  |  | 178.16 |  |  | 485.95 |  |  | 254 |  |  | 271
WORK PACKAGE |  |  | Hour/s worked | Labor Cost | Laptop DV | Hour/s worked | Labor Cost | Laptop DV | Hour/s worked | Labor Cost | Laptop DV | Hour/s worked | Labor Cost | Laptop DV | Hour/s worked | Labor Cost | Laptop DV | Hour/s worked | Labor Cost | Laptop DV | Total Laboor Cost
Choosing Project Client | 3 | 24
1st meeting w/ Client | 1 | 8
Choosing Project Adviser/Consultant | 4 | 32
1st meeting w/ Adviser | 1 | 8
Kick-off Meeting (Sprint 1) | 1 | 8 | 2 | 682 | 75.1285 | 2 | 826 | 49.1452 | 2 | 356.32 | 46.3889 | 2 | 971.9 | 14.932 | [6 empty] | 2836.22
2nd meeting w/ Client | 1 | 8 | 2 | 682 | 75.1285 | 2 | 826 | 49.1452 | 2 | 356.32 | 46.3889 | 2 | 971.9 | 14.932 | [6 empty] | 2836.22
2nd meeting w/ Adviser | 1 | 8 | 2 | 682 | 75.1285 | 2 | 826 | 49.1452 | 2 | 356.32 | 46.3889 | 2 | 971.9 | 14.932 | [6 empty] | 2836.22
Initial Creation of Project Proposal | 12 | 96 | 32 | 10912 | 1202.0566 | 32 | 13216 | 786.3229 | 32 | 5701.12 | 742.2222 |  | 0 | 0 | [6 empty] | 29829.12
3rd meeting w/ Adviser | 1 | 8 | 2 | 682 | 75.1285 | 2 | 826 | 49.1452 | 2 | 356.32 | 46.3889 | 2 | 971.9 | 14.932 | [6 empty] | 2836.22
1st meeting w/ Consultant | 1 | 8 | 2 | 682 | 75.1285 | 2 | 826 | 49.1452 | 2 | 356.32 | 46.3889 |  | 0 | 0 | [6 empty] | 1864.32
Proofreading | 3 | 24 | 8 | 2728 | 300.5141 | 8 | 3304 | 196.5807 | 8 | 1425.28 | 185.5556 |  | 0 | 0 | [6 empty] | 7457.28
Iniitial Project Proposal Evaluation (Sprint 2) | 1 | 8 | 2 | 682 | 75.1285 | 2 | 826 | 49.1452 | 2 | 356.32 | 46.3889 |  | 0 | 0 | [6 empty] | 1864.32
Progression of Project Proposal | 14 | 112 | 37 | 12617 | 1389.8779 | 37 | 15281 | 909.1858 | 37 | 6591.92 | 858.1944 |  | 0 | 0 | [6 empty] | 34489.92
4th Meeting w/ Adviser | 1 | 8 | 2 | 682 | 75.1285 | 2 | 826 | 49.1452 | 2 | 356.32 | 46.3889 |  | 0 | 0 | [6 empty] | 1864.32
Proofreading | 7 | 56 | 15 | 5115 | 563.464 | 15 | 6195 | 368.5888 | 15 | 2672.4 | 347.9167 |  | 0 | 0 | [6 empty] | 13982.4
Final Project Proposal Evaluation (Sprint 3) | 1 | 8 | 2 | 682 | 75.1285 | 2 | 826 | 49.1452 | 2 | 356.32 | 46.3889 |  | 0 | 0 | [6 empty] | 1864.32
Project Charter | 3 | 24 | 8 | 2728 | 300.5141 | 8 | 3304 | 196.5807 | 8 | 1425.28 | 185.5556 |  | 0 | 0 | [6 empty] | 7457.28
Business Case | 3 | 24 | 8 | 2728 | 300.5141 | 8 | 3304 | 196.5807 | 8 | 1425.28 | 185.5556 |  | 0 | 0 | [6 empty] | 7457.28
Stakeholders Management Strategy Plan | 3 | 24 | 8 | 2728 | 300.5141 | 8 | 3304 | 196.5807 | 8 | 1425.28 | 185.5556 |  | 0 | 0 | [6 empty] | 7457.28
Scope Management Plan | 5 | 40 | 8 | 2728 | 300.5141 | 8 | 3304 | 196.5807 | 8 | 1425.28 | 185.5556 |  | 0 | 0 | [6 empty] | 7457.28
Cost Management Plan | 5 | 40 | 10 | 3410 | 375.6427 | 10 | 4130 | 245.7259 | 10 | 1781.6 | 231.9444 |  | 0 | 0 | [6 empty] | 9321.6
Schedule Management Plan | 5 | 40 | 8 | 2728 | 300.5141 | 8 | 3304 | 196.5807 | 8 | 1425.28 | 185.5556 |  | 0 | 0 | [6 empty] | 7457.28
Work Breakdown Structure | 5 | 40 | 10 | 3410 | 375.6427 | 10 | 4130 | 245.7259 | 10 | 1781.6 | 231.9444 |  | 0 | 0 | [6 empty] | 9321.6
Work Packages based on WBS | 5 | 40 | 10 | 3410 | 375.6427 | 10 | 4130 | 245.7259 | 10 | 1781.6 | 231.9444 |  | 0 | 0 | [6 empty] | 9321.6
HR Management Plan | 3 | 24 | 8 | 2728 | 300.5141 | 8 | 3304 | 196.5807 | 8 | 1425.28 | 185.5556 |  | 0 | 0 | [6 empty] | 7457.28
Quality Management Plan | 3 | 24 | 8 | 2728 | 300.5141 | 8 | 3304 | 196.5807 | 8 | 1425.28 | 185.5556 |  | 0 | 0 | [6 empty] | 7457.28
Risk Management Plan | 3 | 24 | 8 | 2728 | 300.5141 | 8 | 3304 | 196.5807 | 8 | 1425.28 | 185.5556 |  | 0 | 0 | [6 empty] | 7457.28
Communications Management Plan | 3 | 24 | 8 | 2728 | 300.5141 | 8 | 3304 | 196.5807 | 8 | 1425.28 | 185.5556 |  | 0 | 0 | [6 empty] | 7457.28
Procurement Management Plan | 3 | 24 | 8 | 2728 | 300.5141 | 8 | 3304 | 196.5807 | 8 | 1425.28 | 185.5556 |  | 0 | 0 | [6 empty] | 7457.28
Implementation Plan | 4 | 32 | 8 | 2728 | 300.5141 | 8 | 3304 | 196.5807 | 8 | 1425.28 | 185.5556 |  | 0 | 0 | [6 empty] | 7457.28
Change Management Plan | 7 | 56 | 8 | 2728 | 300.5141 | 8 | 3304 | 196.5807 | 8 | 1425.28 | 185.5556 |  | 0 | 0 | [6 empty] | 7457.28
Project Managemnt Plan Evaluation (Sprint 4) | 1 | 8 | 2 | 682 | 75.1285 | 2 | 826 | 49.1452 | 2 | 356.32 | 46.3889 |  | 0 | 0 | [6 empty] | 1864.32
Project Management Plan Progression | 7 | 56 | 16 | 5456 | 601.0283 | 16 | 6608 | 393.1614 | 16 | 2850.56 | 371.1111 |  | 0 | 0 | [6 empty] | 14914.56
Finalizing Project Management Plan (Sprint 5) | 1 | 8 | 2 | 682 | 75.1285 | 2 | 826 | 49.1452 | 2 | 356.32 | 46.3889 |  | 0 | 0 | [6 empty] | 1864.32
Creation of Initial Wireframe | 10 | 80 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 20 | 9719 | 149.3205 | 20 | 5080 | 202.9514 |  |  |  | 14799
Creation of UI/UX Design | 15 | 120 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 50 | 24297.5 | 373.3011 | 40 | 10160 | 405.9028 |  |  |  | 34457.5
Initial Protoype Evaluation (Sprint 6) | 1 | 8 |  | 0 | 0 | 2 | 826 | 49.1452 |  | 0 | 0 | 2 | 971.9 | 14.932 | 2 | 508 | 20.2951 |  |  |  | 2305.9
Prototype Progression | 10 | 80 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 30 | 14578.5 | 223.9807 | 30 | 7620 | 304.4271 |  |  |  | 22198.5
Finalization of Initial Protoptype (Sprint 7) | 1 | 8 |  | 0 | 0 | 2 | 826 | 49.1452 |  | 0 | 0 | 2 | 971.9 | 14.932 | 2 | 508 | 20.2951 |  |  |  | 2305.9
Event Table | 4 | 32 | 8 | 2728 | 300.5141 | 8 | 3304 | 196.5807 | 8 | 1425.28 | 185.5556 |  | 0 | 0 |  | 0 | 0 |  |  |  | 7457.28
Use Case Diagram | 5 | 40 | 10 | 3410 | 375.6427 | 10 | 4130 | 245.7259 | 10 | 1781.6 | 231.9444 |  | 0 | 0 |  | 0 | 0 |  |  |  | 9321.6
Use Case Full Description | 5 | 40 | 8 | 2728 | 300.5141 | 8 | 3304 | 196.5807 | 8 | 1425.28 | 185.5556 | 8 | 3887.6 | 59.7282 |  | 0 | 0 |  |  |  | 11344.88
Data Flow Diagram | 5 | 40 | 10 | 3410 | 375.6427 | 10 | 4130 | 245.7259 | 10 | 1781.6 | 231.9444 | 10 | 4859.5 | 74.6602 |  | 0 | 0 |  |  |  | 14181.1
Context Flow Diagram | 3 | 24 | 6 | 2046 | 225.3856 | 6 | 2478 | 147.4355 | 6 | 1068.96 | 139.1667 |  | 0 | 0 |  | 0 | 0 |  |  |  | 5592.96
ERD | 5 | 40 | 10 | 3410 | 375.6427 | 10 | 4130 | 245.7259 | 10 | 1781.6 | 231.9444 | 10 | 4859.5 | 74.6602 |  | 0 | 0 |  |  |  | 14181.1
5th meeting w/ Adviser | 1 | 8 | 2 | 682 | 75.1285 | 2 | 826 | 49.1452 | 2 | 356.32 | 46.3889 | 2 | 971.9 | 14.932 |  | 0 | 0 |  |  |  | 2836.22
6th meeting w/ Adviser | 1 | 8 | 2 | 682 | 75.1285 | 2 | 826 | 49.1452 | 2 | 356.32 | 46.3889 | 2 | 971.9 | 14.932 |  | 0 | 0 |  |  |  | 2836.22
Activity Diagram | 3 | 24 | 6 | 2046 | 225.3856 | 6 | 2478 | 147.4355 | 6 | 1068.96 | 139.1667 |  | 0 | 0 |  | 0 | 0 |  |  |  | 5592.96
Object Diagram | 2 | 16 | 5 | 1705 | 187.8213 | 5 | 2065 | 122.8629 | 5 | 890.8 | 115.9722 |  | 0 | 0 |  | 0 | 0 |  |  |  | 4660.8
Class Diagram | 2 | 16 | 5 | 1705 | 187.8213 | 5 | 2065 | 122.8629 | 5 | 890.8 | 115.9722 |  | 0 | 0 |  | 0 | 0 |  |  |  | 4660.8
Sequence Diagram | 5 | 40 | 10 | 3410 | 375.6427 | 10 | 4130 | 245.7259 | 10 | 1781.6 | 231.9444 | 10 | 4859.5 | 74.6602 |  | 0 | 0 |  |  |  | 14181.1
State Machine Diagram | 2 | 16 | 4 | 1364 | 150.2571 | 4 | 1652 | 98.2904 | 4 | 712.64 | 92.7778 |  | 0 | 0 |  | 0 | 0 |  |  |  | 3728.64
3rd meeting w/ Client | 1 | 8 | 2 | 682 | 75.1285 | 2 | 826 | 49.1452 | 2 | 356.32 | 46.3889 | 2 | 971.9 | 14.932 |  | 0 | 0 |  |  |  | 2836.22
Package Diagram | 3 | 24 | 6 | 2046 | 225.3856 | 6 | 2478 | 147.4355 | 6 | 1068.96 | 139.1667 |  | 0 | 0 |  | 0 | 0 |  |  |  | 5592.96
Deployment Diagram | 2 | 16 | 3 | 1023 | 112.6928 | 3 | 1239 | 73.7178 | 3 | 534.48 | 69.5833 | 3 | 1457.85 | 22.3981 |  | 0 | 0 |  |  |  | 4254.33
Component Diagram | 3 | 24 | 6 | 2046 | 225.3856 | 6 | 2478 | 147.4355 | 6 | 1068.96 | 139.1667 |  | 0 | 0 |  | 0 | 0 |  |  |  | 5592.96
7th meeting w/ Adviser | 1 | 8 | 2 | 682 | 75.1285 | 2 | 826 | 49.1452 | 2 | 356.32 | 46.3889 | 2 | 971.9 | 14.932 |  | 0 | 0 |  |  |  | 2836.22
Project Diagram Evaluation (Sprint 8) | 1 | 8 | 2 | 682 | 75.1285 | 2 | 826 | 49.1452 | 2 | 356.32 | 46.3889 | 2 | 971.9 | 14.932 |  | 0 | 0 |  |  |  | 2836.22
Project Digrams Progressions | 3 | 24 | 6 | 2046 | 225.3856 | 6 | 2478 | 147.4355 | 6 | 1068.96 | 139.1667 | 4 | 1943.8 | 29.8641 |  | 0 | 0 |  |  |  | 7536.76
Finalization of Project Diagrams (Sprint 9) | 1 | 8 | 2 | 682 | 75.1285 | 2 | 826 | 49.1452 | 2 | 356.32 | 46.3889 | 2 | 971.9 | 14.932 |  | 0 | 0 |  |  |  | 2836.22
1st Team development meeting | 1 | 8 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 2 | 971.9 | 14.932 | 2 | 508 | 20.2951 | 2 | 542 | 40.5424 | 2021.9
Creation of Landing Page | 5 | 40 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 15 | 7289.25 | 111.9903 | 15 | 3810 | 152.2135 |  | 0 | 0 | 11099.25
Creation of Contact Page | 3 | 24 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 10 | 4859.5 | 74.6602 | 10 | 2540 | 101.4757 |  | 0 | 0 | 7399.5
Creation of Safety Section Page | 3 | 24 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 10 | 4859.5 | 74.6602 | 10 | 2540 | 101.4757 |  | 0 | 0 | 7399.5
Creation of About Us Page | 1 | 8 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 3 | 1457.85 | 22.3981 | 3 | 762 | 30.4427 |  | 0 | 0 | 2219.85
2nd Team development meeting | 1 | 8 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 2 | 971.9 | 14.932 | 2 | 508 | 20.2951 | 2 | 542 | 40.5424 | 2021.9
Creation of Registration Page | 3 | 24 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 8 | 3887.6 | 59.7282 | 10 | 2540 | 101.4757 |  | 0 | 0 | 6427.6
Creation of Login Page | 3 | 24 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 10 | 4859.5 | 74.6602 | 10 | 2540 | 101.4757 |  | 0 | 0 | 7399.5
Creation of Resident Dashboard | 10 | 80 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 20 | 9719 | 149.3205 | 40 | 10160 | 405.9028 |  | 0 | 0 | 19879
3rd Team development meeting | 1 | 8 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 2 | 971.9 | 14.932 | 2 | 508 | 20.2951 | 2 | 542 | 40.5424 | 2021.9
Creation of Admin Login Page | 3 | 24 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 10 | 4859.5 | 74.6602 | 10 | 2540 | 101.4757 |  | 0 | 0 | 7399.5
Creation of Barangay Administrator Dashboard | 15 | 120 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 50 | 24297.5 | 373.3011 | 60 | 15240 | 608.8542 |  | 0 | 0 | 39537.5
Creation of Managing Barangay Employee Account | 10 | 80 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 30 | 14578.5 | 223.9807 | 40 | 10160 | 405.9028 |  | 0 | 0 | 24738.5
Creation of Barangay Employee Dashboards | 12 | 96 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 40 | 19438 | 298.6409 | 50 | 12700 | 507.3785 |  | 0 | 0 | 32138
4th Team development meeting | 1 | 8 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 2 | 971.9 | 14.932 | 2 | 508 | 20.2951 | 2 | 542 | 40.5424 | 2021.9
8th Team meeting w/ Adviser | 1 | 8 |  | 0 | 0 | 2 | 826 | 49.1452 |  | 0 | 0 | 2 | 971.9 | 14.932 | 2 | 508 | 20.2951 | 2 | 542 | 40.5424 | 2847.9
Release 1 Evaluation (Sprint 10) | 1 | 8 |  | 0 | 0 | 2 | 826 | 49.1452 |  | 0 | 0 | 2 | 971.9 | 14.932 | 2 | 508 | 20.2951 | 2 | 542 | 40.5424 | 2847.9
Release 1 Progression | 20 | 160 |  | 0 | 0 | 20 | 8260 | 491.4518 |  | 0 | 0 | 50 | 24297.5 | 373.3011 | 50 | 12700 | 507.3785 |  | 0 | 0 | 45257.5
Finalizing Release 1 (Sprint 11) | 1 | 8 |  | 0 | 0 | 2 | 826 | 49.1452 |  | 0 | 0 | 2 | 971.9 | 14.932 | 2 | 508 | 20.2951 | 2 | 542 | 40.5424 | 2847.9
Creation of functions to request documents | 15 | 120 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 30 | 14578.5 | 223.9807 | 80 | 20320 | 811.8056 |  | 0 | 0 | 34898.5
Creation of functions to track requested documents | 8 | 64 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 30 | 14578.5 | 223.9807 | 30 | 7620 | 304.4271 |  | 0 | 0 | 22198.5
Creation of functions for notifications | 3 | 24 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 10 | 4859.5 | 74.6602 | 10 | 2540 | 101.4757 |  | 0 | 0 | 7399.5
Creation of functions to manage requested documents | 10 | 80 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 40 | 19438 | 298.6409 | 40 | 10160 | 405.9028 |  | 0 | 0 | 29598
4th Team meeting Team meeting w/ Client | 1 | 8 |  | 0 | 0 | 2 | 826 | 49.1452 |  | 0 | 0 | 2 | 971.9 | 14.932 | 2 | 508 | 20.2951 | 2 | 542 | 40.5424 | 2847.9
Release 2 Evaluation (Sprint 12) | 1 | 8 |  | 0 | 0 | 2 | 826 | 49.1452 |  | 0 | 0 | 2 | 971.9 | 14.932 | 2 | 508 | 20.2951 | 2 | 542 | 40.5424 | 2847.9
Release 2 Progression | 10 | 80 |  | 0 | 0 | 10 | 4130 | 245.7259 |  | 0 | 0 | 30 | 14578.5 | 223.9807 | 30 | 7620 | 304.4271 |  | 0 | 0 | 26328.5
Finalizing Release 2 (Sprint 13) | 1 | 8 |  | 0 | 0 | 2 | 826 | 49.1452 |  | 0 | 0 | 2 | 971.9 | 14.932 | 2 | 508 | 20.2951 | 2 | 542 | 40.5424 | 2847.9
5th Team development meeting | 1 | 8 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 2 | 971.9 | 14.932 | 2 | 508 | 20.2951 | 2 | 542 | 40.5424 | 2021.9
Creation of functions to submit concerns | 10 | 80 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 30 | 14578.5 | 223.9807 | 30 | 7620 | 304.4271 |  | 0 | 0 | 22198.5
Creation of functions to manage concerns | 5 | 40 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 15 | 7289.25 | 111.9903 | 15 | 3810 | 152.2135 |  | 0 | 0 | 11099.25
Creation of functions to track submitted concerns | 2 | 16 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 8 | 3887.6 | 59.7282 | 8 | 2032 | 81.1806 |  | 0 | 0 | 5919.6
Generate Report | 3 | 24 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 12 | 5831.4 | 89.5923 | 12 | 3048 | 121.7708 |  | 0 | 0 | 8879.4
Modify Web App information | 2 | 16 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 8 | 3887.6 | 59.7282 | 8 | 2032 | 81.1806 |  | 0 | 0 | 5919.6
5th Team meeting w/ Client | 1 | 8 |  | 0 | 0 | 2 | 826 | 49.1452 |  | 0 | 0 | 2 | 971.9 | 14.932 | 2 | 508 | 20.2951 | 2 | 542 | 40.5424 | 2847.9
Release 3 Evaluation (Sprint 14) | 1 | 8 |  | 0 | 0 | 2 | 826 | 49.1452 |  | 0 | 0 | 2 | 971.9 | 14.932 | 2 | 508 | 20.2951 | 2 | 542 | 40.5424 | 2847.9
Release 3 Progression | 5 | 40 |  | 0 | 0 | 5 | 2065 | 122.8629 |  | 0 | 0 | 15 | 7289.25 | 111.9903 | 15 | 3810 | 152.2135 |  | 0 | 0 | 13164.25
Finalizing Release 3 (Sprint 15) | 1 | 8 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 2 | 971.9 | 14.932 | 2 | 508 | 20.2951 | 2 | 542 | 40.5424 | 2021.9
Unit Testing for Release 1 | 5 | 40 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 40 | 10840 | 810.8471 | 10840
Unit Testing for Release 2 | 5 | 40 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 40 | 10840 | 810.8471 | 10840
Unit Testing for Release 3 | 5 | 40 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 40 | 10840 | 810.8471 | 10840
User Acceptance Test | 3 | 24 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 24 | 6504 | 486.5083 | 6504
Integration Testing | 3 | 24 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 24 | 6504 | 486.5083 | 6504
Performance Testing | 4 | 32 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 32 | 8672 | 648.6777 | 8672
Verified use cases with the client (Sprint 16) | 1 | 8 | 2 | 682 | 75.1285 | 2 | 826 | 49.1452 |  | 0 | 0 | 2 | 971.9 | 14.932 |  | 0 | 0 | 2 | 542 | 40.5424 | 3021.9
Setting up hosting services | 3 | 24 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 8 | 3887.6 | 59.7282 | 8 | 2032 | 81.1806 | 8 | 2168 | 162.1694 | 8087.6
Go Live (Sprint 17) | 1 | 8 |  | 0 | 0 | 2 | 826 | 49.1452 |  | 0 | 0 | 2 | 971.9 | 14.932 | 2 | 508 | 20.2951 | 2 | 542 | 40.5424 | 2847.9
Session 1 | 1 | 8 | 3 | 1023 | 112.6928 | 3 | 1239 | 73.7178 | 3 | 534.48 | 69.5833 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 2796.48
Session 2 | 1 | 8 | 3 | 1023 | 112.6928 | 3 | 1239 | 73.7178 | 3 | 534.48 | 69.5833 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 2796.48
Session 3 | 1 | 8 | 3 | 1023 | 112.6928 | 3 | 1239 | 73.7178 | 3 | 534.48 | 69.5833 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 2796.48
Finalizing Web App Training Session (Sprint 18) | 1 | 8 | 3 | 1023 | 112.6928 | 3 | 1239 | 73.7178 | 3 | 534.48 | 69.5833 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 2796.48
System and documentation handover | 1 | 8 | 2 | 682 | 75.1285 | 2 | 826 | 49.1452 | 2 | 356.32 | 46.3889 | 2 | 971.9 | 14.932 |  | 0 | 0 |  | 0 | 0 | 2836.22
Gain Formal Acceptance | 1 | 8 | 2 | 682 | 75.1285 | 2 | 826 | 49.1452 | 2 | 356.32 | 46.3889 | 2 | 971.9 | 14.932 |  | 0 | 0 |  | 0 | 0 | 2836.22
Project close out meeting (Sprint 19) | 1 | 8 | 2 | 682 | 75.1285 | 2 | 826 | 49.1452 | 2 | 356.32 | 46.3889 | 2 | 971.9 | 14.932 | 2 | 508 | 20.2951 | 2 | 542 | 40.5424 | 3886.22
TOTAL | 429 | 3432 | 389 | 132649 | 14612.5 | 446 | 184198 | 10959.375 | 387 | 68947.92 | 8976.25 | 699 | 339679.05 | 5218.75 | 720 | 182880 | 7306.25 | 242 | 65582 | 4905.625 | 973935.97

## COSTING
Barangay South Signal Village Web App
Project Duration (months) |  |  |  | 17
PROJECT COST ELEMENTS
Estimated Labor Cost
Role | Hourly Rate (Php) |  | Number of working hours | Total
Project Manager | 341 |  | 389 | 132649
Product Owner | 413 |  | 446 | 184198
Scrum Master / Developer | 485.95 |  | 699 | 339679.05
Laravel Junior Developer | 254 |  | 720 | 182880
QA Tester | 271 |  | 242 | 65582
Documentation Manager | 178.16 |  | 387 | 68947.92
System Trainer | 120 |  | 36 | 4320
Total Estimated Labor Cost |  |  |  | 978255.97
Maintenance Estimated Cost
Managed SSL Services (Go Daddy) | 4999 | yearly |  | 4999
Managed Standard DV SSL Certificate
Expert support
Automated installation, ongoing maintenance and updates
Boosts Google® rankings.
Strong SHA-2 & 2048-bit encryption.
Website Security (Premuim) | 799 | monthly |  | 9588
HTTPS encryption with an SSL
Unlimited prioritized site cleanups and repair.﻿
200 GB of secure daily backup
DDoS protection, and Content Deliver Network (CDN) speed boost.﻿
Firewall helps prevent hackers.
SSL certificate included in firewall.
Daily malware scanning.
Continuous site monitoring with daily alerts and updates.
Website Backup | 99 | monthly |  | 1188
Automatic daily backups
Built-in daily malware scanning
Back up a file, folder or an entire database
Scheduled or on-demand backups
Continuous security monitoring
Downloads to local storage
Easy one-click restore
Secure cloud storage
Expert 24/7 customer support
Maintenace (yearly) |  |  |  | 15775
Hosting and DNS Cost
Hosting w/ DNS protection (36 months) | 12992.72 | every 3 years |  | 12992.72
Expert hosting support.
Web Application Firewall (WAF) prevents hackers and blocks attacks.
Install, configure your SSL, and redirect to https.
Update mixed content errors, sitemap, and firewall settings.
Free domain
Easy-to-use control panel.
Linux Web Hosting (75 GB NVMe SSD Storage, 2 shared CPUs, 1.5 GB memory, 50 GB MySQL databases, phpMyAdmin, CloudLinux, SSH access (secure shell), FTP over SSL (FTPS), Site statisticsPremium DNS, PHP 8.1, 8.0, 7.4, 7.3, 5.6, Custom PHP.ini, HTTP/2, Python, Perl, Web mail, Fraud, virus & spam protection, Email privacy & protection with 256-bit encryption)
Estimated Depreciation Expenses
| Current Value (after depriacted by years) |  | Depr. Value (25%)
Mikedale Dellera (Laptop) | 35000 |  | 14612.5
Princess Joy Ferrer (Laptop) | 21500 |  | 8976.25
Wilkins Caducio (Laptop) | 26250 |  | 10959.375
Jakerson Bermudo (Laptop) | 12500 |  | 5218.75
Carl James Garcia (Laptop) | 11750 |  | 4905.625
Rark Mowen Alcantara (Laptop) | 17500 |  | 7306.25
Estimated Depreciation Expenses |  |  |  | 51978.75
Indirect Cost
Utilities | Covered by the barangay
Equipment
Internet
Training Supplies
Miscellaneous expenses
Estimated Project Cost |  |  | 1059002.44
Maintenace (yearly) |  |  | 15775

## Sheet1
Summary Milestone Schedule – List key project milestones relative to project start.
Project Milestone
Target Date
(mm/dd/yyyy)
PROJECT START | 03/30/2022
PLANNING
- Kick-off Meeting (Sprint 1) | 4/14/2022
- Initial Project Proposal Evaluation (Sprint 2) | 5/17/2022
- Final Project Proposal Evaluation (Sprint 3) | 6/20/2022
- Project Management Plan Evaluation (Sprint 4) | 9/14/2022
- Finalizing Project Management Plan (Sprint 5) | 10/26/2022
ANALYSIS AND DESIGN
- Initial Prototype Evaluation (Sprint 6) | 12/23/2022
- Finalization of Initial Prototype (Sprint 7) | 12/16/2022
- Project Diagram Evaluation (Sprint 8) | 1/16/2023
- Finalization of Project Diagrams (Sprint 9) | 1/20/2023
DEVELOPMENT
- Release 1 Evaluation (Sprint 10) | 2023-12-05
- Finalizing Release 1 (Sprint 11) | 2023-12-06
- Release 2 Evaluation (Sprint 12) | 2023-07-08
- Finalizing Release 2 (Sprint 13) | 8/22/2023
- Release 3 Evaluation (Sprint 14) | 9/26/2023
- Finalizing Release 3 (Sprint 15) | 2023-04-10
TESTING
- Verified use cases with the client (Sprint 16) | 10/27/23
IMPLEMENTATION
- Go Live (Sprint 17) | 2023-02-11
- Finalizing Web App Training Session (Sprint 18) | 11/27/2023
CLOSEOUT
- Project close out meeting (Sprint 19) | 11/30/2023

## BENEFIT
Estimated Benefit
Estimated Number of Requests per year | 70000
Estimated revenue from requesting documents | 50
Estimated Average Benefit every year | 3500000

## COST-BENEFIT ANALYSIS
Estimated increase per yer: | 1.1
100 % No Error | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7
Benefit | 3500000 | 3850000 | 4235000 | 4658500 | 5124350 | 5636785 | 6200463.5
Cost | 1059002.44 | 15775 | 15775 | 28767.72 | 15775 | 15775 | 28767.72
Estimated Savings | 2440997.56 | 6275222.56 | 4219225 | 4629732.28 | 5108575 | 5621010 | 6171695.78