## Sheet1
Level 2 | Level 3 | Level 4 | Level 5
1.1 Planning | 1.1.1 Project Preparation | 1.1.1.1 Creation of Project Team
| 1.1.2 Initial Project Proposal | 1.1.1.2 Choosing Project Client
| 1.1.3 Progression of Project Proposal | 1.1.1.3 1st meeting w/Client
| 1.1.4 Creation of Project Management Plans | 1.1.1.4 Choosing Project Adviser/ Consultant
1.1.1.5 1st meeting w/Adviser
1.1.1.6 Kick-off meeting (Sprint 1)
1.1.2.1 2nd meeting w/ Client
1.1.2.2 2nd meeting w/ Adviser
1.1.2.3 Chapter 1 (Introduction)
1.1.2.4 Chapter 2 (RRL/RRS)
1.1.2.5 Chapter 3 (Methodology)
1.1.2.6 Chapter 4 (Results and Discussions)
1.1.2.7 Chapter 5 (Conclusion)
1.1.2.8 Proofreading
1.1.2.9 Initial Project Proposal Evaluation (Sprint 2)
1.1.3.1 Chapter 1 (Introduction)
1.1.3.2 Chapter 2 (RRL/RRS)
1.1.3.3 Chapter 3 (Current System)
1.1.3.4 Chapter 4 (Proposed System)
1.1.3.5 Chapter 5 (Requirement Analysis)
1.1.3.6 Chapter 6 (Conclusion)
1.1.3.7 Proofreading
1.1.3.8 Finalizing Project Proposal
1.1.3.9 Final Project Proposal Evaluation (Sprint 3)
1.1.4.1 Project Charter
1.1.4.2 Business Case
1.1.4.3 Stakeholders Management Strategy Plan
1.1.4.4 Scope Management Plan
1.1.4.5 Cost Management Plan
1.1.4.6 Time Management Plan
1.1.4.7 Work Breakdown Structure
1.1.4.8 Work Packages based on WBS
1.1.4.9 HR Management Plan
1.1.4.10 Quality Management Plan
1.1.4.11 Risk Management Plan
1.1.4.12 Communications Management Plan
1.1.4.13 Procurement Management Plan
1.1.4.14 Implementation Plan
1.1.4.15 Change Management Plan
1.1.4.16 Project Managemnt Plan Evaluation (Sprint 4)
1.1.4.17 Project Management Plan Progression
1.1.4.18 Finalizing Project Management Plan (Sprint 5)
1.2 Analysis and Design | 1.2.1 Creation of Initial Prototype | 1.2.1.1 Creation of Initial Wireframe
| 1.2.2 Creation of Project Diagrams | 1.2.1.2 Creation of UI/UX Design
1.2.1.3 Initial Protoype Evaluation (Sprint 6)
1.2.1.4 Prototype Progression
1.2.1.5 Finalization of Initial Protoptype (Sprint 7)
1.2.2.1 Event Table
1.2.2.2 Use Case Diagram
1.2.2.3 Use Case Full Description
1.2.2.4 Data Flow Diagram
1.2.2.5 Context Flow Diagram
1.2.2.6 ERD
1.2.2.7 5th meeting w/Adviser
1.2.2.8 6th meeting w/Adviser
1.2.2.9 Activity Diagram
1.2.2.10 Object Diagram
1.2.2.11 Class Diagram
1.2.2.12 Sequence Diagram
1.2.2.13 State Machine Diagram
1.2.2.14 3rd meeting w/Client
1.2.2.15 Package Diagram
1.2.2.16 Deployment Diagram
1.2.2.17 Component Diagram
1.2.2.18 7th meeting w/ Adviser
1.2.2.19 Project Diagram Evaluation (Sprint 8)
1.2.2.20 Project Digrams Progressions
1.2.2.21 Finalization of Project Diagrams (Sprint 9)
1.3 Development | 1.3.1 Release 1 | 1.3.1.1 Main Page Feature | 1.3.1.1.1 1st Team development meeting
| 1.3.2 Release 2 | 1.3.1.2 Resident Dashboard | 1.3.1.1.2 Creation of Landing Page
| 1.3.3 Release 3 | 1.3.1.3 Barangay Employee Dashboard | 1.3.1.1.3 Creation of Contact Page
|  | 1.3.1.4 4th Team development meeting | 1.3.1.1.4 Creation of Safety Section Page
|  | 1.3.1.5 8th Team meeting w/ Adviser | 1.3.1.1.5 Creation of About Us Page
|  | 1.3.1.6 Release 1 Evaluation (Sprint 10) | 1.3.1.1.6 2nd Team development meeting
|  | 1.3.1.7 Release 1 Progression | 1.3.1.2.1 Creation of Registration Page
|  | 1.3.1.8 Finalizing Release 1 (Sprint 11) | 1.3.1.2.2 Creation of Login Page
|  | 1.3.2.1 Requesting Barangay Documents | 1.3.1.2.3 Creation of Resident Dashboard
|  | 1.3.2.2 4th Team meeting Team meeting w/ Client | 1.3.1.2.4 3rd Team development meeting
|  | 1.3.2.3 Release 2 Evaluation (Sprint 12) | 1.3.1.3.1 Creation of Admin Login Page
|  | 1.3.2.3 Release 2 Progression | 1.3.1.2.2 Creation of Barangay Administrator Dashboard
|  | 1.3.2.5 Finalizing Release 2 (Sprint 13) | 1.3.1.2.3 Creation of Managing Barangay Employee Account
|  | 1.3.2.6 5th Team development meeting | 1.3.1.2.4 Creation of Barangay Employee Dashboards
|  | 1.3.3.1 Submitting Concerns | 1.3.2.1.1 Creation of functions to request documents
|  | 1.3.3.2 Manage Web App | 1.3.2.1.2 Creation of functions to track requested documents
|  | 1.3.3.3 5th Team meeting w/ Client | 1.3.2.1.3 Creation of functions for notifications
|  | 1.3.3.4 Release 3 Evaluation (Sprint 14) | 1.3.2.1.4 Creation of functions to manage requested documents
|  | 1.3.3.5 Release 3 Progression | 1.3.3.1.1 Creation of functions to submit concerns
|  | 1.3.3.6 Finalizing Release 3 (Sprint 15) | 1.3.3.1.2 Creation of functions to manage concerns
1.3.3.1.3 Creation of functions to track submitted concerns
1.3.3.2.1 Generate Report
1.3.3.2.2 Modify Web App information.
1.4 Testing | 1.4 1 Unit Testing | 1.4.1.1 Unit Testing for Release 1
| 1.4.2 User Acceptance Test | 1.4.1.2 Unit Testing for Release 2
| 1.4.3 Integration Testing | 1.4.1.3 Unit Testing for Release 3
1.4.4 Performance Testing
1.4.5 Verified use cases with the client (Sprint 16)
1.5 Implementation | 1.5.1 Hosting | 1.5.1.1 Setting up hosting services
| 1.5.2 Web App Training w/ client | 1.5.1.2 Go Live (Sprint 17)
1.5.2.1 Session 1
1.5.2.2 Session 2
1.5.2.3 Session 3
1.5.2.4 Finalizing Web App Training Session (Sprint 18)
1.6 Closeout | 1.6.1 System and documentation handover
1.6.2 Gain Formal Acceptance
1.6.3 Project close out meeting (Sprint 19)