## WBS
Level | WBS Code | Element Name | TIME
1 | 1 | Barangay South Signal Village Web App
2 | 1.1 | Planning | 87
3 | 1.1.1 | Project Preparation | 23
4 | 1.1.1.1 | Creation of Project Groups | 4 | dale
4 | 1.1.1.2 | Choose Project/Client | 4 | jake
4 | 1.1.1.3 | Choose Adviser/Consultant | 20 | wilkins
4 | 1.1.1.4 | Design Thinking 1 | 3 | carl
3 | 1.1.2 | MNTSDEV Team consultation | 7
4 | 1.1.2.1 | Team meeting with Project adviser | 5 | rark
4 | 1.1.2.2 | Team meeting with Project Sponsor | 2 | dale
3 | 1.1.3 | MNTSDEV Creation of Midterm Paper | 15
4 | 1.1.3.1 | Chapter 1 (Introduction) | 12 | jake
4 | 1.1.3.2 | Chapter 2 (RRL/RRS) | 12 | wilkins
4 | 1.1.3.3 | Chapter 3 (Methodology) | 12 | carl
4 | 1.1.3.4 | Chapter 4 (Results and Discussions) | 12 | rark
4 | 1.1.3.5 | Chapter 5 (Conclusion) | 1 | dale
4 | 1.1.3.6 | Proofreading | 1 | jake
4 | 1.1.3.7 | Creation of presentation deck | 1 | wilkins
3 | 1.1.4 | MNTSDEV Midterm Evaluation | 7
4 | 1.1.4.1 | Midterm (Sprint1) | 1 | carl
4 | 1.1.4.2 | Comment Matrix | 5 | rark
3 | 1.1.5 | Initial Design | 44
4 | 1.1.5.1 | Initial wireframe | 14 | dale
4 | 1.1.5.2 | Initial low-fidelity prototype | 24 | jake
3 | 1.1.6 | MNTSDEV Progression of Paper/Final Paper | 25
4 | 1.1.6.1 | Chapter 1 (Introduction) | 22 | wilkins
4 | 1.1.6.2 | Chapter 2 (RRL/RRS) | 22 | carl
4 | 1.1.6.3 | Chapter 3 (Current System) | 22 | rark
4 | 1.1.6.4 | Chapter 4 (Proposed System) | 22 | dale
4 | 1.1.6.5 | Chapter 5 (Requirement Analysis) | 22 | jake
4 | 1.1.6.6 | Chapter 6 (Conclusion) | 1 | wilkins
4 | 1.1.6.7 | Proofreading | 1 | carl
4 | 1.1.6.8 | Creation of presentation deck | 1 | rark
4 | 1.1.6.9 | Submission of final Requirements for Final Presentation | 1 | dale
3 | 1.1.7 | MNSTDEV Finals Evaluation | 21
4 | 1.1.7.1 | Final Presentation (Sprint 2) | 1 | jake
4 | 1.1.7.2 | Revision for Comment Matrix and Final Paper | 19 | wilkins
4 | 1.1.7.3 | Submission of MNSTDEV FINAL Documents | 1 | carl
2 | 1.2 | Analysis and Design | 171
3 | 1.2.1 | MSYADD Project Progression | 88
4 | 1.2.1.1 | Initial analysis for Chapter 5 (Requirement Analysis) | 22 | rark
4 | 1.2.1.2 | Submission of MNSTDEV final documents | 5 | dale
4 | 1.2.1.3 | Implementation of GitHub Repository | 1 | jake
4 | 1.2.1.4 | Request letter for Adviser/Consultant | 5 | wilkins
3 | 1.2.2 | MSYADD Team consultation | 4
4 | 1.2.2.1 | Team meeting with Project adviser | 3 | carl
4 | 1.2.2.2 | Team meeting with Project Sponsor | 1 | rark
3 | 1.2.3 | MSYADD Individual Deliverables | 31
3 | 1.2.4 | MSYADD Release Plan | 73
4 | 1.2.4.1 | Release Plan 1.1 | 31 | dale
4 | 1.2.4.2 | Release Plan 1.2 | 35 | jake
3 | 1.2.5 | MSYADD Week 3 - Week 4 | 11
4 | 1.2.5.1 | Event Table | 2 | wilkins
4 | 1.2.5.2 | Use Case Diagram | 2 | carl
4 | 1.2.5.3 | Use Case Full Description | 2 | rark
4 | 1.2.5.4 | Data Flow Diagram | 1 | dale
4 | 1.2.5.5 | Context Flow Diagram | 2 | jake
4 | 1.2.5.6 | Entity Relationship Diagram | 2 | wilkins
3 | 1.2.6 | MSYADD Week 5 - Week 7 | 10
4 | 1.2.6.1 | Activity Diagram | 5 | carl
4 | 1.2.6.2 | Object Diagram | 3 | rark
4 | 1.2.6.3 | Class Diagram | 2 | dale
3 | 1.2.7 | MSYADD Midterm Evaluation | 5
4 | 1.2.7.1 | Pre-midterm Presentation (Sprint 3) | 1 | jake
4 | 1.2.7.2 | Midterm Presentation (Sprint 4) | 1 | wilkins
4 | 1.2.7.3 | Revision Midterm | 3 | carl
3 | 1.2.8 | MSYADD Week 8 - Week 9 | 10.125
4 | 1.2.8.1 | Sequence Diagram | 2.4 | rark
4 | 1.2.8.2 | State Machine Diagram | 2.4 | dale
4 | 1.2.8.3 | Package Diagram | 2.4 | jake
4 | 1.2.8.4 | Deployment Diagram | 2.4 | wilkins
4 | 1.2.8.5 | Component Diagram | 2.4 | carl
3 | 1.2.9 | MSYADD Final Evaluation | 14
4 | 1.2.9.1 | MSYADD Pre-final Presentation (Sprint 5) | 4 | rark
4 | 1.2.9.2 | MSYADD Final Presentation (Sprint 6) | 1 | dale
4 | 1.2.9.3 | Revision for Final Paper | 7 | jake
4 | 1.2.9.4 | Submission of Final Requirements | 1 | wilkins
2 | 1.3 | DEVELOPMENT | 417
3 | 1.3.1 | MCSPROJ Project Progression | 7
4 | 1.3.1.1 | Submission of MSYADD Final Documents | 7 | carl
4 | 1.3.1.2 | Request letter for Adviser/Consultant | 7 | rark
3 | 1.3.2 | MCSPROJ Release Plan | 193
4 | 1.3.2.1 | Finalizing Release 1 | 73 | dale
4 | 1.3.2.2 | Release Plan 2 | 46 | jake
4 | 1.3.2.3 | Release Plan 3 | 49 | wilkins
3 | 1.3.3 | MCSPROJ Midterm Deliverables | 36
4 | 1.3.3.1 | Creation of Gantt Chart | 8 | carl
4 | 1.3.3.2 | Creation of WBS | 1 | rark
4 | 1.3.3.3 | Creation of Activity List | 1 | dale
4 | 1.3.3.4 | Creation of Project Vision and Scope Progression | 25 | jake
4 | 1.3.3.5 | Creation of Statement of Work Progression | 25 | wilkins
4 | 1.3.3.6 | Creation of Project Charter Progression | 25 | carl
4 | 1.3.3.7 | Pre-midterm Presentation (Sprint 7) | 1 | rark
3 | 1.3.4 | MCSPROJ Team consultation | 2
4 | 1.3.4.1 | Team meeting with Project adviser | 1 | dale
4 | 1.3.4.2 | Team meeting with Project Sponsor | 1 | jake
3 | 1.3.5 | MCSPROJ Midterm Evaluation | 2
4 | 1.3.5.1 | Submission of Midterm Requirement | 1 | wilkins
4 | 1.3.5.2 | MCSPROJ Final Presentation (Sprint 8) | 1 | carl
3 | 1.3.6 | MCSPROJ Finals Deliverables | 49
4 | 1.3.6.1 | Creation of Test Case | 49 | rark
4 | 1.3.6.2 | Creation of Quality Plan | 49 | dale
4 | 1.3.6.3 | Creation of User Acceptance | 49 | jake
4 | 1.3.6.4 | Creation of Change Management Plan | 49 | wilkins
4 | 1.3.6.5 | Updating MCSPROJ Final Paper | 32 | carl
4 | 1.3.6.6 | Creation of Proofreading Endorsement | 32 | rark
3 | 1.3.7 | MCSPROJ Finals Evaluation | 1
4 | 1.3.7.1 | Submission of MCSPROJ Final Requirements | 1 | dale
4 | 1.3.7.2 | MCSPROJ Final Presentation (Sprint 9) | 1 | jake
2 | 1.4 | Implementation | 461
3 | 1.4.1 | PROJMAN Project Progression | 1
4 | 1.4.1.1 | Submission of MCSPROJ Final Documents | 1 | wilkins
4 | 1.4.1.2 | Request Letter for Adviser/Consultant | 1 | carl
3 | 1.4.2 | PROJMAN Week 1-3 | 17
4 | 1.4.2.1 | Creation of Project Charter | 17 | rark
4 | 1.4.2.2 | Creation of Business Case | 17 | dale
4 | 1.4.2.3 | Creation of Stakeholders Management Strategy Plan | 17 | jake
3 | 1.4.3 | PROJMAN Week 4-6 | 19
4 | 1.4.3.1 | Creation of Scope Management Plan | 19 | wilkins
4 | 1.4.3.2 | Creation of Cost Management Plan | 19 | carl
4 | 1.4.3.3 | Creation of Time Management Plan | 19 | rark
4 | 1.4.3.4 | Creation of Work Breakdown Structure | 19 | dale
4 | 1.4.3.5 | Creation of Work Packages based on WBS. | 19 | jake
3 | 1.4.4 | System Updates | 5
4 | 1.4.4.1 | Testing 1 | 5 | wilkins
3 | 1.4.5 | PROJMAN Midterm Evaluation | 1
4 | 1.4.5.1 | Submission of PROJMAN Midterm Requirements | 1 | carl
4 | 1.4.5.2 | PROJMAN Midterm presentation (Sprint 10) | 1 | rark
3 | 1.4.6 | PROJMAN Week 8-10 | 18
4 | 1.4.6.1 | Creation of HR Management Plan | 18 | dale
4 | 1.4.6.2 | Creation of Quality Management Plan | 18 | jake
4 | 1.4.6.3 | Creation of Risk Management Plan | 18 | wilkins
4 | 1.4.6.4 | Creation of Communications Management Plan | 18 | carl
4 | 1.4.6.5 | Creation of Procurement Management Plan | 18 | rark
3 | 1.4.7 | PROJMAN Week 11 | 4
4 | 1.4.7.1 | Creation of Project Status Reports Distribution Plan | 4 | dale
4 | 1.4.7.2 | Creation of Change Request Documentation | 4 | jake
4 | 1.4.7.3 | Creation of Project Execution Monitoring Report | 4 | wilkins
4 | 1.4.7.4 | Creation of Implementation Plan | 4 | carl
3 | 1.4.8 | PROJMAN Week 12 | 7
4 | 1.4.8.1 | Creation of Change Management Plan | 7 | rark
4 | 1.4.8.2 | Creation of Project Status Reports | 7 | dale
4 | 1.4.8.3 | Creation of Transition-Out Plan | 7 | jake
4 | 1.4.8.4 | Creation of Project Turn-Over Plan | 7 | wilkins
4 | 1.4.8.5 | Creation of Post Project Review Plan | 7 | carl
3 | 1.4.9 | PROJMAN Week 13 | 6
4 | 1.4.9.1 | Creation of Consolidated Project Plan | 6 | rark
3 | 1.4.10 | PROJMAN Final Evaluation | 1
4 | 1.4.10.1 | Submission of PROJMAN Final Requirements | 1 | dale
4 | 1.4.10.2 | PROJMAN Final presentation (Sprint 11) | 1 | jake
3 | 1.4.11 | Closeout | 1
4 | 1.4.11.1 | System and documentation handover (Sprint 12) | 1 | wilkins
4 | 1.4.11.2 | Gain Formal Acceptance | 1 | carl
4 | 1.4.11.3 | Project close out meeting | 1 | rark

## wbs - cost format
Level | WBS Code | Element Name | Definition | Estimated Duration | Expected Labor Cost
[5 empty] | Project Manager | Product Owner | Scrum Master | Scrum Member/s | Documentation Manager
[5 empty] | 316.28 | 365.63 | 496.88 | 250 | 256.62
1 | 1 | Barangay South Signal Village Web App | A web application developed for the use of Barangay South Signal Village in addressing their local governance needs
2 | 1.1 | PLANNING |  | 87 days
3 | 1.1.1 | Project Preparation | The phase of the planning stage that includes activities such as creating project groups, choosing project/client, selecting an adviser/consultant, and initiating design thinking. | 23 days | 58195.75 | 67275 | 91425 | 46000 | 47217.85
4 | 1.1.1.1 | Creation of Project Groups | The process of creating teams or groups of individuals that will be responsible for specific tasks and activities in the development of the web application. | 4 days
4 | 1.1.1.2 | Choose Project/Client | The process of selecting a project or client for whom the web application will be developed. | 4 days
4 | 1.1.1.3 | Choose Adviser/Consultant | The process of selecting a qualified adviser or consultant who will provide guidance and support to the project team in developing the web application. | 20 days
4 | 1.1.1.4 | Design Thinking 1 | A human-centered approach to problem-solving that involves empathizing with the users, defining the problem, solutions, and prototyping. | 3 days | ₱7,590.72 | ₱8,775.12 | ₱11,925.12 | ₱6,000.00 | ₱6,158.88
3 | 1.1.2 | MNTSDEV Team consultation | Meeting of the project team to discuss progress, issues, and updates. | 7 days | 17711.75 | 20475 | 27825 | 14000 | 14370.65
4 | 1.1.2.1 | Team meeting with Project adviser | Meeting with the project team and the project adviser to discuss issues and concerns regarding the development of the web application. | 5 days
4 | 1.1.2.2 | Team meeting with Project Sponsor | Meeting with the project team with the project sponsor to provide updates on project progress and receive feedback on project deliverables. | 2 days
3 | 1.1.3 | MNTSDEV Creation of Midterm Paper | A document that outlines the progress of the web application development project and includes a detailed analysis of the project's strengths and weaknesses. | 15 days | 37953.75 | 43875 | 59625 | 30000 | 30794.25
4 | 1.1.3.1 | Chapter 1 (Introduction) | The first chapter of the midterm paper, which includes the background of the project, the project objectives, and the project scope. | 12 days
4 | 1.1.3.2 | Chapter 2 (RRL/RRS) | The second chapter of the midterm paper that includes a review of related literature and studies | 12 days
4 | 1.1.3.3 | Chapter 3 (Methodology) | The third chapter of the midterm paper that includes a description of the methodology used for the project | 12 days | ₱30,362.88 | ₱35,100.48 | ₱47,700.48 | ₱24,000.00 | ₱24,635.52
4 | 1.1.3.4 | Chapter 4 (Results and Discussions) | The fourth chapter of the midterm paper that includes the results and discussions of the web application project | 12 days
4 | 1.1.3.5 | Chapter 5 (Conclusion) | The fifth and final chapter of the midterm paper that includes the conclusion of the web application project | 1 day
4 | 1.1.3.6 | Proofreading | A task that involves reviewing and correcting errors in the project documents and deliverables | 1 day
4 | 1.1.3.7 | Creation of presentation deck | A task that involves creating a presentation deck for the web application project | 1 day
3 | 1.1.4 | MNTSDEV Midterm Evaluation | Evaluation of the project progress and status | 7 days | 17711.75 | 20475 | 27825 | 14000 | 14370.65
4 | 1.1.4.1 | Midterm (Sprint1) | Development of the project during the first sprint | 1 days | ₱2,530.24 | ₱2,925.04 | ₱3,975.04 | ₱2,000.00 | ₱2,052.96
4 | 1.1.4.2 | Comment Matrix | Document containing feedback and comments on the project. | 5 days
3 | 1.1.5 | Initial Design | Creation of the initial design of the web application | 44 days |  |  | 174900 | 88000
4 | 1.1.5.1 | Initial wireframe | Creation of the initial wireframe of the web application | 14 days
4 | 1.1.5.2 | Initial low-fidelity prototype | Creation of the first prototype with basic functionality | 25 days
3 | 1.1.6 | MNTSDEV Progression of Paper/Final Paper | The process of developing and improving the final paper, which includes all chapters, results, and discussions. | 22 days | 63256.25 | 73125 | 99375 | 50000 | 51323.75
4 | 1.1.6.1 | Chapter 1 (Introduction) | The first chapter of the final paper, which provides an overview of the research problem, objectives, and scope. | 22 days
4 | 1.1.6.2 | Chapter 2 (RRL/RRS) | The second chapter of the final paper, which presents the related literature and related research studies. | 22 days | ₱55,665.28 | ₱64,350.88 | ₱87,450.88 | ₱44,000.00 | ₱45,165.12
4 | 1.1.6.3 | Chapter 3 (Current System) | The third chapter of the final paper, which describes the existing system or technology related to the research. | 22 days
4 | 1.1.6.4 | Chapter 4 (Proposed System) | The fourth chapter of the final paper, which presents the proposed system or technology to be developed. | 22 days
4 | 1.1.6.5 | Chapter 5 (Requirement Analysis) | The fifth chapter of the final paper, which presents the requirements and specifications of the proposed system. | 22 days
4 | 1.1.6.6 | Chapter 6 (Conclusion) | The last chapter of the final paper, which summarizes the research and provides recommendations for future work. | 1 day
4 | 1.1.6.7 | Proofreading | The process of checking the final paper for any errors or mistakes, such as spelling, grammar, and formatting. | 1 day | ₱2,530.24 | ₱2,925.04 | ₱3,975.04 | ₱2,000.00 | ₱2,052.96
4 | 1.1.6.8 | Creation of presentation deck | A task that involves creating a presentation deck for the web application project | 1 day
4 | 1.1.6.9 | Submission of final Requirements for Final Presentation | The process of submitting all necessary requirements for the final presentation. | 1 day
3 | 1.1.7 | MNSTDEV Finals Evaluation | The evaluation process of the final presentation and the final paper. | 21 days | 53135.25 | 61425 | 83475 | 42000 | 43111.95
4 | 1.1.7.1 | Final Presentation (Sprint 2) | The presentation of the final paper to an audience, which includes the project adviser and panelists | 1 day
4 | 1.1.7.2 | Revision for Comment Matrix and Final Paper | The process of revising the final paper and the comment matrix is based on the feedback from the evaluation. | 19 days
4 | 1.1.7.3 | Submission of MNSTDEV FINAL Documents | The process of submitting the final paper and all necessary documents to complete the final deliverables | 1 day | ₱2,530.24 | ₱2,925.04 | ₱3,975.04 | ₱2,000.00 | ₱2,052.96
2 | 1.2 | ANALYSIS AND DESIGN |  | 171 days
3 | 1.2.1 | MSYADD Project Progression | Refers to the overall progress and development of the MSYADD project. | 88 days | 222662 |  |  |  | 180659.6
4 | 1.2.1.1 | Initial analysis for Chapter 5 (Requirement Analysis) | The process of analyzing the requirements needed for Chapter 5 of the MSYADD project. | 22 days
4 | 1.2.1.2 | Submission of MNSTDEV final documents | Submission of the final documents required for the MNSTDEV | 5 day
4 | 1.2.1.3 | Implementation of GitHub Repository | Setting up the GitHub repository for the project | 1 days
4 | 1.2.1.4 | Request letter for Adviser/Consultant | Formal request for an adviser or consultant for the MSYADD project. | 5 days
3 | 1.2.2 | MSYADD Team consultation | Meeting with the project team to discuss progress, issues, and updates. | 4 days | 10121 | 11700 | 15900 | 8000 | 8211.8
4 | 1.2.2.1 | Team meeting with Project adviser | Meeting with the project team and the project adviser to discuss issues and concerns regarding the development of the web application. | 3 days | ₱7,590.72 | ₱8,775.12 | ₱11,925.12 | ₱6,000.00 | ₱6,158.88
4 | 1.2.2.2 | Team meeting with Project Sponsor | Meeting with the project team with the project sponsor to provide updates on project progress and receive feedback on project deliverables. | 1 day
3 | 1.2.3 | MSYADD Individual Deliverables | Submission of individual deliverables for the MSYADD project. | 31 days | 78437.75 | 90675 | 123225 | 62000 | 63641.45
3 | 1.2.4 | MSYADD Release Plan | A plan that outlines the timeline for the release of a new version of the MSYADD project | 73 days |  | 213525 | 290175 | 146000
4 | 1.2.4.1 | Release Plan 1.1 | A specific release of the MSYADD project that includes new features or improvements | 31 days
4 | 1.2.4.2 | Release Plan 1.2 | Another specific release of the MSYADD project that includes new features or improvements | 35 days
3 | 1.2.5 | MSYADD Week 3 - Week 4 | The period of time during the MSYADD project when certain tasks are expected to be completed | 11 days | 27832.75 | 32175 | 43725 | 22000 | 22582.45
4 | 1.2.5.1 | Event Table | A table that documents events and their attributes | 2 days
4 | 1.2.5.2 | Use Case Diagram | A visual representation of the interactions between actors and the system in a particular use case scenario | 2 days | ₱5,060.48 | ₱5,850.08 | ₱7,950.08 | ₱4,000.00 | ₱4,105.92
4 | 1.2.5.3 | Use Case Full Description | A detailed description of each use case | 2 days
4 | 1.2.5.4 | Data Flow Diagram | A visual representation of the flow of data through a system or process | 1 day
4 | 1.2.5.5 | Context Flow Diagram | A high-level data flow diagram that provides an overview of the entire system or process | 2 days
4 | 1.2.5.6 | Entity Relationship Diagram | A visual representation of the relationships between entities in a database | 2 days
3 | 1.2.6 | MSYADD Week 5 - Week 7 | The period of time during the MSYADD project when certain tasks are expected to be completed | 10 days | 25302.5 | 29250 | 39750 | 20000 | 20529.5
4 | 1.2.6.1 | Activity Diagram | A visual representation of the flow of activities or actions in a particular process or system | 5 days | ₱12,651.20 | ₱14,625.20 | ₱19,875.20 | ₱10,000.00 | ₱10,264.80
4 | 1.2.6.2 | Object Diagram | A visual representation of the objects and their relationships in a system | 3 days
4 | 1.2.6.3 | Class Diagram | A visual representation of the classes, their attributes, and their relationships in an object-oriented programming language | 2 days
3 | 1.2.7 | MSYADD Midterm Evaluation | Evaluation of the project progress and status | 5 days | 12651.25 | 14625 | 19875 | 10000 | 10264.75
4 | 1.2.7.1 | Pre-midterm Presentation (Sprint 3) | Presentation of the progress made on the MSYADD project before the midterm evaluation | 1 day
4 | 1.2.7.2 | Midterm Presentation (Sprint 4) | Presentation of the progress made on the MSYADD project | 1 day
4 | 1.2.7.3 | Revision Midterm | Revising the project based on the feedback and evaluation received during the midterm presentation. | 3 days | ₱7,590.72 | ₱8,775.12 | ₱11,925.12 | ₱6,000.00 | ₱6,158.88
3 | 1.2.8 | MSYADD Week 8 - Week 9 | Timeframe for completing the Sequence Diagram, State Machine Diagram, Package Diagram, Deployment Diagram, and Component Diagram. | 10.125 days | 25618.78 | 29615.63 | 40246.88 | 20250 | 20786.12
4 | 1.2.8.1 | Sequence Diagram | Shows the interactions between objects in a system over time. | 2.4 days
4 | 1.2.8.2 | State Machine Diagram | Depicts the states and transitions of an object or system. | 2.4 days
4 | 1.2.8.3 | Package Diagram | Displays the organization of various elements in a system into related groups. | 2.4 days
4 | 1.2.8.4 | Deployment Diagram | Shows the physical arrangement of hardware and software components in a system. | 2.4 days
4 | 1.2.8.5 | Component Diagram | Illustrates the components and relationships of components within a system. | 2.4 days | ₱6,072.58 | ₱7,020.10 | ₱9,540.10 | ₱4,800.00 | ₱4,927.10
3 | 1.2.9 | MSYADD Final Evaluation | The final evaluation of the MSYADD project. | 14 days | 35423.5 | 40950 | 55650 | 28000 | 28741.3
4 | 1.2.9.1 | MSYADD Pre-final Presentation (Sprint 5) | A presentation of the progress made on the MSYADD project before the final evaluation | 4 days
4 | 1.2.9.2 | MSYADD Final Presentation (Sprint 6) | The final presentation of the MSYADD project | 1 day
4 | 1.2.9.3 | Revision for Final Paper | Revising the project paper based on the feedback received during the final evaluation. | 7 days
4 | 1.2.9.4 | Submission of Final Requirements | The final submission of all project requirement/deliverables, including the project paper and presentation. | 1 day
2 | 1.3 | DEVELOPMENT |  | 417 days
3 | 1.3.1 | MCSPROJ Project Progression | Refers to the overall progress and development of the MCSPROJ project. | 7 days | 17711.75 | 20475 | 27825 | 14000 | 14370.65
4 | 1.3.1.1 | Submission of MSYADD Final Documents | Submission of the final documents required for the MSYADD | 7 days | ₱17,711.68 | ₱20,475.28 | ₱27,825.28 | ₱14,000.00 | ₱14,370.72
4 | 1.3.1.2 | Request letter for Adviser/Consultant | Formal request for an adviser or consultant for the MCSPROJ project. | 7 days
3 | 1.3.2 | MCSPROJ Release Plan | A plan that outlines the timeline for the release of a new version of the MCSPROJ project | 193 days | 488338.25 | 564525 | 767175 | 386000
4 | 1.3.2.1 | Finalizing Release 1 | The process of finalizing the first release of the project | 73 days
4 | 1.3.2.2 | Release Plan 2 | A plan for releasing the second version of the project | 46 days
4 | 1.3.2.3 | Release Plan 3 | A plan for releasing the third version of the project | 49 days
3 | 1.3.3 | MCSPROJ Midterm Deliverables | The deliverables that need to be completed by the midterm of the project | 36 days | 91089 | 105300 | 143100 | 72000 | 73906.2
4 | 1.3.3.1 | Creation of Gantt Chart | Creating a Gantt chart to track the progress of the project | 8 days | ₱20,241.92 | ₱23,400.32 | ₱31,800.32 | ₱16,000.00 | ₱16,423.68
4 | 1.3.3.2 | Creation of WBS | Creating a Work Breakdown Structure to break down the project into smaller tasks | 1 day
4 | 1.3.3.3 | Creation of Activity List | Creating a list of activities that need to be completed for the project | 1 day
4 | 1.3.3.4 | Creation of Project Vision and Scope Progression | Progressing the project vision and scope to a more detailed level | 25 days
4 | 1.3.3.5 | Creation of Statement of Work Progression | Progressing the statement of work to a more detailed level | 25 days
4 | 1.3.3.6 | Creation of Project Charter Progression | Progressing the project charter to a more detailed level | 25 days | ₱63,256.00 | ₱73,126.00 | ₱99,376.00 | ₱50,000.00 | ₱51,324.00
4 | 1.3.3.7 | Pre-midterm Presentation (Sprint 7) | A presentation of the project's progress and accomplishments before the midterm presentation | 1 day
3 | 1.3.4 | MCSPROJ Team consultation | Meeting with the project team to discuss progress, issues, and updates. | 2 days | 5060.5 | 5850 | 7950 | 4000 | 4105.9
4 | 1.3.4.1 | Team meeting with Project adviser | Meeting with the project team and the project adviser to discuss issues and concerns regarding the development of the web application. | 1 day
4 | 1.3.4.2 | Team meeting with Project Sponsor | Meeting with the project team with the project sponsor to provide updates on project progress and receive feedback on project deliverables. | 1 day
3 | 1.3.5 | MCSPROJ Midterm Evaluation | An evaluation of the project's progress and accomplishments at the halfway point of the project | 2 days | 5060.5 | 5850 | 7950 | 4000 | 4105.9
4 | 1.3.5.1 | Submission of Midterm Requirement | Submission of required deliverables at the midterm evaluation | 1 day
4 | 1.3.5.2 | MCSPROJ Final Presentation (Sprint 8) | A presentation of the final project product, its features, and its benefits | 1 day | ₱2,530.24 | ₱2,925.04 | ₱3,975.04 | ₱2,000.00 | ₱2,052.96
3 | 1.3.6 | MCSPROJ Finals Deliverables | Required deliverables for the final project product, including test cases, quality plans, user acceptance, change management plans, updated final paper, and proofreading endorsement | 49 days | 123982.25 | 143325 | 194775 | 98000 | 100594.55
4 | 1.3.6.1 | Creation of Test Case | Creation of a set of conditions or variables under which a tester will determine whether an application or software system meets its requirements and works correctly | 49 days
4 | 1.3.6.2 | Creation of Quality Plan | Creation plan that outlines the quality standards and processes that will be used in the project | 49 days
4 | 1.3.6.3 | Creation of User Acceptance | Create of a set of tests to confirm that the system satisfies the user's needs and meets the requirements | 49 days
4 | 1.3.6.4 | Creation of Change Management Plan | Creation that describes how changes to the project will be handled | 49 days
4 | 1.3.6.5 | Updating MCSPROJ Final Paper | Updating the final project paper to reflect any changes made during the project | 32 days | ₱80,967.68 | ₱93,601.28 | ₱127,201 | ₱64,000.00 | ₱65,694.72
4 | 1.3.6.6 | Creation of Proofreading Endorsement | An endorsement that confirms that the final project paper has been reviewed and proofread | 32 days
3 | 1.3.7 | MCSPROJ Finals Evaluation | The final evaluation of the MCSPROJ project. | 1 day | 2530.25 | 2925 | 3975 | 2000 | 2052.95
4 | 1.3.7.1 | Submission of MCSPROJ Final Requirements | The final submission of all project requirement/deliverables, including the working system | 1 day
4 | 1.3.7.2 | MCSPROJ Final Presentation (Sprint 9) | A final presentation of the project product and its benefits to stakeholders. | 1 day
2 | 1.4 | IMPLEMENTATION |  | 461 days
3 | 1.4.1 | PROJMAN Project Progression | Refers to the overall progress and development of the PROJMAN project. | 1 day | 2530.25 | 2925 | 3975 | 2000 | 2052.95
4 | 1.4.1.1 | Submission of MCSPROJ Final Documents | Submission of the final documents required for the MCSPROJ | 1 day
4 | 1.4.1.2 | Request Letter for Adviser/Consultant | Formal request for an adviser or consultant for the PROJMAN project. | 1 day | ₱2,530.24 | ₱2,925.04 | ₱3,975.04 | ₱2,000.00 | ₱2,052.96
3 | 1.4.2 | PROJMAN Week 1-3 | Timeframe for completing the Project Charter, Business Case, Stakeholders Management Strategy Plan | 17 days | 43014.25 | 49725 | 67575 | 34000 | 34900.15
4 | 1.4.2.1 | Creation of Project Charter | The process of defining the project's purpose, objectives, and stakeholders, and establishing the project's authority | 17 days
4 | 1.4.2.2 | Creation of Business Case | The process of identifying and analyzing the benefits, costs, and risks associated with a project | 17 days
4 | 1.4.2.3 | Creation of Stakeholders Management Strategy Plan | The process of identifying, analyzing, and planning the communication and management of stakeholders throughout the project lifecycle | 17 days
3 | 1.4.3 | PROJMAN Week 4-6 | Timeframe for completing the Scope Management Plan, Cost Management Plan, Time Management Plan, Work Breakdown Structure, and Work Breakdown Packages | 19 days | 48074.75 | 55575 | 75525 | 38000 | 39006.05
4 | 1.4.3.1 | Creation of Scope Management Plan | The process of defining, documenting, and controlling the project scope, including the deliverables and requirements | 19 days
4 | 1.4.3.2 | Creation of Cost Management Plan | The process of planning, estimating, and controlling project costs, including budgeting and cost tracking | 19 days | ₱48,074.56 | ₱55,575.76 | ₱75,525.76 | ₱38,000.00 | ₱39,006.24
4 | 1.4.3.3 | Creation of Time Management Plan | The process of defining and sequencing project activities, developing and assigning schedules, and monitoring progress | 19 days
4 | 1.4.3.4 | Creation of Work Breakdown Structure | A hierarchical breakdown of project deliverables into smaller, manageable components | 19 days
4 | 1.4.3.5 | Creation of Work Packages based on WBS. | A process of creating smaller, more manageable components from the work breakdown structure | 19 days
3 | 1.4.4 | System Updates | The process of updating the project's software and hardware, ensuring that it remains up-to-date and functional | 5 days | 12651.25 | 14625 | 19875 | 10000 | 10264.75
4 | 1.4.4.1 | Testing 1 | A phase of software development where the software is tested for defects, errors, and usability issues | 5 days
3 | 1.4.5 | PROJMAN Midterm Evaluation | An evaluation of the project's progress and accomplishments at the halfway point of the project | 1 day | 2530.25 | 2925 | 3975 | 2000 | 2052.95
4 | 1.4.5.1 | Submission of PROJMAN Midterm Requirements | Submission of required deliverables at the midterm evaluation | 1 day | ₱2,530.24 | ₱2,925.04 | ₱3,975.04 | ₱2,000.00 | ₱2,052.96
4 | 1.4.5.2 | PROJMAN Midterm presentation (Sprint 10) | Presentation given during the midterm stage of the PROJMAN project. | 1 day
3 | 1.4.6 | PROJMAN Week 8-10 | Timeframe for completing the HR Management Plan, Quality Management Plan, Risk Management Plan, Communications Management Plan, and Procurement Management Plan | 18 days | 45544.5 | 52650 | 71550 | 36000 | 36953.1
4 | 1.4.6.1 | Creation of HR Management Plan | Develop a plan to manage human resources for the project | 18 days
4 | 1.4.6.2 | Creation of Quality Management Plan | Develop a plan to ensure the quality of project deliverables | 18 days
4 | 1.4.6.3 | Creation of Risk Management Plan | Develop a plan to identify, assess, and mitigate project risks | 18 days
4 | 1.4.6.4 | Creation of Communications Management Plan | Develop a plan for project communications, including stakeholders and team members | 18 days | ₱45,544.32 | ₱52,650.72 | ₱71,550.72 | ₱36,000.00 | ₱36,953.28
4 | 1.4.6.5 | Creation of Procurement Management Plan | Develop a plan that outlines the procurement processes and procedures that will be implemented throughout the project. | 18 days
3 | 1.4.7 | PROJMAN Week 11 | Timeframe for completing the Project Status Reports Distribution Plan, Change Request Documentation, Project Execution Monitoring Report, and Implementation Plan | 18 days | 10121 | 11700 | 15900 | 8000 | 8211.8
4 | 1.4.7.1 | Creation of Project Status Reports Distribution Plan | Develop a plan for the distribution of project status reports to stakeholders and team members | 4 days
4 | 1.4.7.2 | Creation of Change Request Documentation | Develop a document to manage changes to project scope, schedule, or budget | 4 days
4 | 1.4.7.3 | Creation of Project Execution Monitoring Report | Develop a report to monitor project progress and identify issues or risks | 4 days
4 | 1.4.7.4 | Creation of Implementation Plan | Develop a plan for implementing project deliverables and closing out the project | 4 days | ₱10,120.96 | ₱11,700.16 | ₱15,900.16 | ₱8,000.00 | ₱8,211.84
3 | 1.4.8 | PROJMAN Week 12 | Timeframe for completing the Change Management Plan, Project Status Reports, Transition-Out Plan, Project Turn-Over Plan, and Post Project Review Plan | 7 days | 17711.75 | 20475 | 27825 | 14000 | 14370.65
4 | 1.4.8.1 | Creation of Change Management Plan | Develop a plan to handle changes that may occur during the project to minimize their impact. | 7 days
4 | 1.4.8.2 | Creation of Project Status Reports | Regularly report on the project's status, including progress, risks, issues, and resource usage. | 7 days
4 | 1.4.8.3 | Creation of Transition-Out Plan | Develop a plan for transitioning the project's deliverables to the stakeholders. | 7 days
4 | 1.4.8.4 | Creation of Project Turn-Over Plan | Develop a plan for transferring ownership of the project to the stakeholders | 7 days
4 | 1.4.8.5 | Creation of Post Project Review Plan | Develop a plan for evaluating the project's performance, identifying lessons learned, and making recommendations for future projects. | 7 days | ₱17,711.68 | ₱20,475.28 | ₱27,825.28 | ₱14,000.00 | ₱14,370.72
3 | 1.4.9 | PROJMAN Week 13 | Timeframe for completing the Consolidated Project Plan | 6 days | 15181.5 | 17550 | 23850 | 12000 | 12317.7
4 | 1.4.9.1 | Creation of Consolidated Project Plan | Process of integrating all project plans (scope, schedule, cost, quality, etc.) into a single, comprehensive project plan | 6 days
3 | 1.4.10 | PROJMAN Final Evaluation | Assessment of the project's overall performance and success at completion | 1 day | 2530.25 | 2925 | 3975 | 2000 | 2052.95
4 | 1.4.10.1 | Submission of PROJMAN Final Requirements | Submission of all final deliverables and requirements as per the project plan | 1 day
4 | 1.4.10.2 | PROJMAN Final presentation (Sprint 11) | A final presentation of the project product and its benefits to stakeholders. | 1 day
2 | 1.5 | CLOSEOUT |  | 3 days
3 | 1.5.1 | System and documentation handover (Sprint 12) | Transfer of the completed system and all relevant documentation to the stakeholders | 1 day | 2530.25 | 2925 | 3975 | 2000 | 2052.95
4 | 1.5.1.1 | System and documentation handover | Transfer of the completed system and all relevant documentation to the stakeholders | 1 day
3 | 1.5.2 | Gain Formal Acceptance | Obtaining formal approval and acceptance from the client or end-user that the project has been completed successfully | 1 day | 2530.25 | 2925 | 3975 | 2000 | 2052.95
4 | 1.5.2.1 | Gain Formal Acceptance | Obtaining formal approval and acceptance from the client or end-user that the project has been completed successfully | 1 day | ₱2,530.24 | ₱2,925.04 | ₱3,975.04 | ₱2,000.00 | ₱2,052.96
3 | 1.5.3 | Project close out meeting | Final meeting held to review the project and discuss lessons learned, celebrate successes, and plan for future improvements | 1 day | 2530.25 | 2925 | 3975 | 2000 | 2052.95
4 | 1.5.3.1 | Project close out meeting | Final meeting held to review the project and discuss lessons learned, celebrate successes, and plan for future improvements | 1 day

## WBS with cost
Level | WBS Code | Element Name | DAYS | Project Manager | Product Owner | Scrum Master | Scrum Member/s | Documentation Manager
SALARY |  |  |  | 316.28 | 365.63 | 496.88 | 250 | 256.62
1 | 1 | Barangay South Signal Village Web App
2 | 1.1 | Planning | 87
3 | 1.1.1 | Project Preparation | 23 | 58195.75 | 67275 | 91425 | 46000 | 47217.85
4 | 1.1.1.1 | Creation of Project Groups | 4
4 | 1.1.1.2 | Choose Project/Client | 4
4 | 1.1.1.3 | Choose Adviser/Consultant | 20 | 50604.8 | 58500.8 | 79500.8 | 40000 | 41059.2
4 | 1.1.1.4 | Design Thinking 1 | 3 | 7590.72 | 8775.12 | 11925.12 | 6000 | 6158.88
3 | 1.1.2 | MNTSDEV Team consultation | 7 | 17711.75 | 20475 | 27825 | 14000 | 14370.65
4 | 1.1.2.1 | Team meeting with Project adviser | 5
4 | 1.1.2.2 | Team meeting with Project Sponsor | 2
3 | 1.1.3 | MNTSDEV Creation of Midterm Paper | 15 | 37953.75 | 43875 | 59625 | 30000 | 30794.25
4 | 1.1.3.1 | Chapter 1 (Introduction) | 12
4 | 1.1.3.2 | Chapter 2 (RRL/RRS) | 12 | 30362.88 | 35100.48 | 47700.48 | 24000 | 24635.52
4 | 1.1.3.3 | Chapter 3 (Methodology) | 12 | 30362.88 | 35100.48 | 47700.48 | 24000 | 24635.52
4 | 1.1.3.4 | Chapter 4 (Results and Discussions) | 12
4 | 1.1.3.5 | Chapter 5 (Conclusion) | 1
4 | 1.1.3.6 | Proofreading | 1
4 | 1.1.3.7 | Creation of presentation deck | 1 | 2530.24 | 2925.04 | 3975.04 | 2000 | 2052.96
3 | 1.1.4 | MNTSDEV Midterm Evaluation | 7 | 17711.75 | 20475 | 27825 | 14000 | 14370.65
4 | 1.1.4.1 | Midterm (Sprint1) | 1 | 2530.24 | 2925.04 | 3975.04 | 2000 | 2052.96
4 | 1.1.4.2 | Comment Matrix | 5
3 | 1.1.5 | Initial Design | 44 |  |  | 174900 | 88000
4 | 1.1.5.1 | Initial wireframe | 14
4 | 1.1.5.2 | Initial low-fidelity prototype | 24
3 | 1.1.6 | MNTSDEV Progression of Paper/Final Paper | 25 | 63256.25 | 73125 | 99375 | 50000 | 51323.75
4 | 1.1.6.1 | Chapter 1 (Introduction) | 22 | 55665.28 | 64350.88 | 87450.88 | 44000 | 45165.12
4 | 1.1.6.2 | Chapter 2 (RRL/RRS) | 22 | 55665.28 | 64350.88 | 87450.88 | 44000 | 45165.12
4 | 1.1.6.3 | Chapter 3 (Current System) | 22
4 | 1.1.6.4 | Chapter 4 (Proposed System) | 22
4 | 1.1.6.5 | Chapter 5 (Requirement Analysis) | 22
4 | 1.1.6.6 | Chapter 6 (Conclusion) | 1 | 2530.24 | 2925.04 | 3975.04 | 2000 | 2052.96
4 | 1.1.6.7 | Proofreading | 1 | 2530.24 | 2925.04 | 3975.04 | 2000 | 2052.96
4 | 1.1.6.8 | Creation of presentation deck | 1
4 | 1.1.6.9 | Submission of final Requirements for Final Presentation | 1
3 | 1.1.7 | MNSTDEV Finals Evaluation | 21 | 53135.25 | 61425 | 83475 | 42000 | 43111.95
4 | 1.1.7.1 | Final Presentation (Sprint 2) | 1
4 | 1.1.7.2 | Revision for Comment Matrix and Final Paper | 19 | 48074.56 | 55575.76 | 75525.76 | 38000 | 39006.24
4 | 1.1.7.3 | Submission of MNSTDEV FINAL Documents | 1 | 2530.24 | 2925.04 | 3975.04 | 2000 | 2052.96
2 | 1.2 | Analysis and Design | 171
3 | 1.2.1 | MSYADD Project Progression | 88 | 222662 |  |  |  | 180659.6
4 | 1.2.1.1 | Initial analysis for Chapter 5 (Requirement Analysis) | 22
4 | 1.2.1.2 | Submission of MNSTDEV final documents | 5
4 | 1.2.1.3 | Implementation of GitHub Repository | 1
4 | 1.2.1.4 | Request letter for Adviser/Consultant | 5 | 12651.2 | 14625.2 | 19875.2 | 10000 | 10264.8
3 | 1.2.2 | MSYADD Team consultation | 4 | 10121 | 11700 | 15900 | 8000 | 8211.8
4 | 1.2.2.1 | Team meeting with Project adviser | 3 | 7590.72 | 8775.12 | 11925.12 | 6000 | 6158.88
4 | 1.2.2.2 | Team meeting with Project Sponsor | 1
3 | 1.2.3 | MSYADD Individual Deliverables | 31 | 78437.75 | 90675 | 123225 | 62000 | 63641.45
3 | 1.2.4 | MSYADD Release Plan | 73 |  | 213525 | 290175 | 146000
4 | 1.2.4.1 | Release Plan 1.1 | 31
4 | 1.2.4.2 | Release Plan 1.2 | 35
3 | 1.2.5 | MSYADD Week 3 - Week 4 | 11 | 27832.75 | 32175 | 43725 | 22000 | 22582.45
4 | 1.2.5.1 | Event Table | 2 | 5060.48 | 5850.08 | 7950.08 | 4000 | 4105.92
4 | 1.2.5.2 | Use Case Diagram | 2 | 5060.48 | 5850.08 | 7950.08 | 4000 | 4105.92
4 | 1.2.5.3 | Use Case Full Description | 2
4 | 1.2.5.4 | Data Flow Diagram | 1
4 | 1.2.5.5 | Context Flow Diagram | 2
4 | 1.2.5.6 | Entity Relationship Diagram | 2 | 5060.48 | 5850.08 | 7950.08 | 4000 | 4105.92
3 | 1.2.6 | MSYADD Week 5 - Week 7 | 10 | 25302.5 | 29250 | 39750 | 20000 | 20529.5
4 | 1.2.6.1 | Activity Diagram | 5 | 12651.2 | 14625.2 | 19875.2 | 10000 | 10264.8
4 | 1.2.6.2 | Object Diagram | 3
4 | 1.2.6.3 | Class Diagram | 2
3 | 1.2.7 | MSYADD Midterm Evaluation | 5 | 12651.25 | 14625 | 19875 | 10000 | 10264.75
4 | 1.2.7.1 | Pre-midterm Presentation (Sprint 3) | 1
4 | 1.2.7.2 | Midterm Presentation (Sprint 4) | 1 | 2530.24 | 2925.04 | 3975.04 | 2000 | 2052.96
4 | 1.2.7.3 | Revision Midterm | 3 | 7590.72 | 8775.12 | 11925.12 | 6000 | 6158.88
3 | 1.2.8 | MSYADD Week 8 - Week 9 | 10.125 | 25618.78 | 29615.63 | 40246.88 | 20250 | 20786.12
4 | 1.2.8.1 | Sequence Diagram | 2.4
4 | 1.2.8.2 | State Machine Diagram | 2.4
4 | 1.2.8.3 | Package Diagram | 2.4
4 | 1.2.8.4 | Deployment Diagram | 2.4 | 6072.576 | 7020.096 | 9540.096 | 4800 | 4927.104
4 | 1.2.8.5 | Component Diagram | 2.4 | 6072.576 | 7020.096 | 9540.096 | 4800 | 4927.104
3 | 1.2.9 | MSYADD Final Evaluation | 14 | 35423.5 | 40950 | 55650 | 28000 | 28741.3
4 | 1.2.9.1 | MSYADD Pre-final Presentation (Sprint 5) | 4
4 | 1.2.9.2 | MSYADD Final Presentation (Sprint 6) | 1
4 | 1.2.9.3 | Revision for Final Paper | 7
4 | 1.2.9.4 | Submission of Final Requirements | 1 | 2530.24 | 2925.04 | 3975.04 | 2000 | 2052.96
2 | 1.3 | DEVELOPMENT | 417
3 | 1.3.1 | MCSPROJ Project Progression | 7 | 17711.75 | 20475 | 27825 | 14000 | 14370.65
4 | 1.3.1.1 | Submission of MSYADD Final Documents | 7 | 17711.68 | 20475.28 | 27825.28 | 14000 | 14370.72
4 | 1.3.1.2 | Request letter for Adviser/Consultant | 7
3 | 1.3.2 | MCSPROJ Release Plan | 193 | 488338.25 | 564525 | 767175 | 386000 | 396219.35
4 | 1.3.2.1 | Finalizing Release 1 | 73
4 | 1.3.2.2 | Release Plan 2 | 46
4 | 1.3.2.3 | Release Plan 3 | 49 | 123981.76 | 143326.96 | 194776.96 | 98000 | 100595.04
3 | 1.3.3 | MCSPROJ Midterm Deliverables | 36 | 91089 | 105300 | 143100 | 72000 | 73906.2
4 | 1.3.3.1 | Creation of Gantt Chart | 8 | 20241.92 | 23400.32 | 31800.32 | 16000 | 16423.68
4 | 1.3.3.2 | Creation of WBS | 1
4 | 1.3.3.3 | Creation of Activity List | 1
4 | 1.3.3.4 | Creation of Project Vision and Scope Progression | 25
4 | 1.3.3.5 | Creation of Statement of Work Progression | 25 | 63256 | 73126 | 99376 | 50000 | 51324
4 | 1.3.3.6 | Creation of Project Charter Progression | 25 | 63256 | 73126 | 99376 | 50000 | 51324
4 | 1.3.3.7 | Pre-midterm Presentation (Sprint 7) | 1
3 | 1.3.4 | MCSPROJ Team consultation | 2 | 5060.5 | 5850 | 7950 | 4000 | 4105.9
4 | 1.3.4.1 | Team meeting with Project adviser | 1
4 | 1.3.4.2 | Team meeting with Project Sponsor | 1
3 | 1.3.5 | MCSPROJ Midterm Evaluation | 2 | 5060.5 | 5850 | 7950 | 4000 | 4105.9
4 | 1.3.5.1 | Submission of Midterm Requirement | 1 | 2530.24 | 2925.04 | 3975.04 | 2000 | 2052.96
4 | 1.3.5.2 | MCSPROJ Final Presentation (Sprint 8) | 1 | 2530.24 | 2925.04 | 3975.04 | 2000 | 2052.96
3 | 1.3.6 | MCSPROJ Finals Deliverables | 49 | 123982.25 | 143325 | 194775 | 98000 | 100594.55
4 | 1.3.6.1 | Creation of Test Case | 49
4 | 1.3.6.2 | Creation of Quality Plan | 49
4 | 1.3.6.3 | Creation of User Acceptance | 49
4 | 1.3.6.4 | Creation of Change Management Plan | 49 | 123981.76 | 143326.96 | 194776.96 | 98000 | 100595.04
4 | 1.3.6.5 | Updating MCSPROJ Final Paper | 32 | 80967.68 | 93601.28 | 127201.28 | 64000 | 65694.72
4 | 1.3.6.6 | Creation of Proofreading Endorsement | 32
3 | 1.3.7 | MCSPROJ Finals Evaluation | 1 | 2530.25 | 2925 | 3975 | 2000 | 2052.95
4 | 1.3.7.1 | Submission of MCSPROJ Final Requirements | 1
4 | 1.3.7.2 | MCSPROJ Final Presentation (Sprint 9) | 1
2 | 1.4 | Implementation | 461 | 1166445.25 | 1348425 | 1832475 | 922000 | 946409.95
3 | 1.4.1 | PROJMAN Project Progression | 1 | 2530.25 | 2925 | 3975 | 2000 | 2052.95
4 | 1.4.1.1 | Submission of MCSPROJ Final Documents | 1 | 2530.24 | 2925.04 | 3975.04 | 2000 | 2052.96
4 | 1.4.1.2 | Request Letter for Adviser/Consultant | 1 | 2530.24 | 2925.04 | 3975.04 | 2000 | 2052.96
3 | 1.4.2 | PROJMAN Week 1-3 | 17 | 43014.25 | 49725 | 67575 | 34000 | 34900.15
4 | 1.4.2.1 | Creation of Project Charter | 17
4 | 1.4.2.2 | Creation of Business Case | 17
4 | 1.4.2.3 | Creation of Stakeholders Management Strategy Plan | 17
3 | 1.4.3 | PROJMAN Week 4-6 | 19 | 48074.75 | 55575 | 75525 | 38000 | 39006.05
4 | 1.4.3.1 | Creation of Scope Management Plan | 19 | 48074.56 | 55575.76 | 75525.76 | 38000 | 39006.24
4 | 1.4.3.2 | Creation of Cost Management Plan | 19 | 48074.56 | 55575.76 | 75525.76 | 38000 | 39006.24
4 | 1.4.3.3 | Creation of Time Management Plan | 19
4 | 1.4.3.4 | Creation of Work Breakdown Structure | 19
4 | 1.4.3.5 | Creation of Work Packages based on WBS. | 19
3 | 1.4.4 | System Updates | 5 | 12651.25 | 14625 | 19875 | 10000 | 10264.75
4 | 1.4.4.1 | Testing 1 | 5 | 12651.2 | 14625.2 | 19875.2 | 10000 | 10264.8
3 | 1.4.5 | PROJMAN Midterm Evaluation | 1 | 2530.25 | 2925 | 3975 | 2000 | 2052.95
4 | 1.4.5.1 | Submission of PROJMAN Midterm Requirements | 1 | 2530.24 | 2925.04 | 3975.04 | 2000 | 2052.96
4 | 1.4.5.2 | PROJMAN Midterm presentation (Sprint 10) | 1
3 | 1.4.6 | PROJMAN Week 8-10 | 18 | 45544.5 | 52650 | 71550 | 36000 | 36953.1
4 | 1.4.6.1 | Creation of HR Management Plan | 18
4 | 1.4.6.2 | Creation of Quality Management Plan | 18
4 | 1.4.6.3 | Creation of Risk Management Plan | 18 | 45544.32 | 52650.72 | 71550.72 | 36000 | 36953.28
4 | 1.4.6.4 | Creation of Communications Management Plan | 18 | 45544.32 | 52650.72 | 71550.72 | 36000 | 36953.28
4 | 1.4.6.5 | Creation of Procurement Management Plan | 18
3 | 1.4.7 | PROJMAN Week 11 | 4 | 10121 | 11700 | 15900 | 8000 | 8211.8
4 | 1.4.7.1 | Creation of Project Status Reports Distribution Plan | 4
4 | 1.4.7.2 | Creation of Change Request Documentation | 4
4 | 1.4.7.3 | Creation of Project Execution Monitoring Report | 4 | 10120.96 | 11700.16 | 15900.16 | 8000 | 8211.84
4 | 1.4.7.4 | Creation of Implementation Plan | 4 | 10120.96 | 11700.16 | 15900.16 | 8000 | 8211.84
3 | 1.4.8 | PROJMAN Week 12 | 7 | 17711.75 | 20475 | 27825 | 14000 | 14370.65
4 | 1.4.8.1 | Creation of Change Management Plan | 7
4 | 1.4.8.2 | Creation of Project Status Reports | 7
4 | 1.4.8.3 | Creation of Transition-Out Plan | 7
4 | 1.4.8.4 | Creation of Project Turn-Over Plan | 7 | 17711.68 | 20475.28 | 27825.28 | 14000 | 14370.72
4 | 1.4.8.5 | Creation of Post Project Review Plan | 7 | 17711.68 | 20475.28 | 27825.28 | 14000 | 14370.72
3 | 1.4.9 | PROJMAN Week 13 | 6 | 15181.5 | 17550 | 23850 | 12000 | 12317.7
4 | 1.4.9.1 | Creation of Consolidated Project Plan | 6
3 | 1.4.10 | PROJMAN Final Evaluation | 1 | 2530.25 | 2925 | 3975 | 2000 | 2052.95
4 | 1.4.10.1 | Submission of PROJMAN Final Requirements | 1
4 | 1.4.10.2 | PROJMAN Final presentation (Sprint 11) | 1
2 | 1.5 | CLOSEOUT | 3
3 | 1.5.1 | System and documentation handover (Sprint 12) | 1 | 2530.24 | 2925.04 | 3975.04 | 2000 | 2052.96
4 | 1.5.1.1 | System and documentation handover (Sprint 12) | 1 | 2530.24 | 2925.04 | 3975.04 | 2000 | 2052.96
3 | 1.5.2 | Gain Formal Acceptance | 1 | 2530.24 | 2925.04 | 3975.04 | 2000 | 2052.96
4 | 1.5.2.1 | Gain Formal Acceptance | 1 | 2530.24 | 2925.04 | 3975.04 | 2000 | 2052.96
3 | 1.5.3 | Project close out meeting | 1 | 2530.24 | 2925.04 | 3975.04 | 2000 | 2052.96
4 | 1.5.3.1 | Project close out meeting | 1
Note on C153: Jakerson Bermudo: